## Biểu đồ Gantt
ViIP-A-GraphRAG
TIÊU ĐỀ DỰ ÁN |  | Vietnamese Intellectual Property Agentic Graph-Augmented RAG
NGƯỜI QUẢN LÝ DỰ ÁN
SỐ CẤU TRÚC PHÂN CHIA CÔNG VIỆC (WBS) | TIÊU ĐỀ CÔNG VIỆC | NGƯỜI PHỤ TRÁCH CÔNG VIỆC |  | NGÀY BẮT ĐẦU | NGÀY ĐẾN HẠN | THỜI GIAN | PHẦN TRĂM CÔNG VIỆC HOÀN THÀNH | Tháng 6 | [13 empty] | Tháng 7 | [27 empty] | Tháng 8
|  |  | Deliverables |  |  |  |  | TUẦN 3 | [6 empty] | TUẦN 4 | [6 empty] | TUẦN 1 | [6 empty] | TUẦN 2 | [6 empty] | TUẦN 3 | [6 empty] | TUẦN 4 | [6 empty] | TUẦN 1 | [6 empty] | TUẦN 2 | [6 empty] | TUẦN 3 | [6 empty] | TUẦN 4
[8 empty] | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN
1 | Data Processing
2018-01-01 | Collect data ("Sỡ hữu trí tuệ") | My, Lý | Raw text dataset isolated from the original legal database. |  |  | 0 | 0%
1.1.1 | Preprocessing - Convert to .md - other preprocessing actions | Bình | Clean text files in .md format, uniform fonts, and removed noise characters. |  |  | 0 | 0%
2018-02-01 | Chunking | Thảo | Hierarchical splitting algorithm (Parent-Child pattern) preserving the Clause-Article structure. |  |  | 0 | 0%
| Data Auditing and Statistics | Kiệt | Token distribution and entity density statistics table for Chapter 4 of the Paper. |  |  |  | 0%
2 | Vector Search
2018-01-02 | Research about Embedding Models | Tên người | A list of efficient and domain-related models (Evaluation report on BGE-M3 vs. Baselines). |  |  | 0 | 0%
2018-02-02 | Embedding Processing | Tên người | Run embedding models on the processed chunks (Generate dense vector matrices from text). |  |  | 0 | 0%
2018-03-02 | Vector Database Indexing & Tuning | Tên người | Initialize Qdrant Collection configuration, optimize HNSW index parameters for real-time search. |  |  | 0 | 0%
3 | Graph Search
3.1 | Schema | Tên người | Technical specifications of property constraints, primary keys, and structural indexes on Graph DB. |  |  | 0 | 0%
3.2 | Ontology | Tên người | Architecture diagram of Nodes (Document, Article, Clause) and Edges (GUIDES, SUPERSEDES, EXPIRED). |  |  | 0 | 0%
3.3 | Knowledge Extraction | Tên người | Raw Triples (A set of semantic legal relationship triplets extracted from the metadata layer). |  |  | 0 | 0%
3.4 | Import KG to Neo4j |  | Execute data import scripts to successfully populate the Neo4j graph database instance. |  |  | 0 | 0%
4 | Hybrid Search
2018-01-04 | Synchronize Vector DB and Graph DB | Tên người | Cross-ID mapping system (Accurately mapping Qdrant Payload IDs to Neo4j Node IDs). |  |  | 0 | 0%
2018-02-04 | Graph-Guided Vector Filtering | Tên người | Backend API logic that queries active legal status on Graph before passing hard strict filters to Vector streams. |  |  | 0 | 0%
2018-03-04 | Latency Optimization | Tên người | Optimize parallel retrieval querying, ensuring overall Hybrid Search stays below 200ms. |  |  | 0 | 0%
5 | Agentic Query Router
| User Intent Classification | Tên người | Semantic query parsing layer classifying user inputs into intent classes (Procedures, Penalties, Validity). |  |  | 0 | 0%
| Dynamic Routing Logic | Tên người | Routing system code implemented in FastAPI to dynamically steer execution streams. |  |  | 0 | 0%
| Error Handling & Fallback Stream | Tên người | Redundancy fallback logic to safely downgrade to vanilla Vector Search if the Graph node traversal fails. |  |  | 0 | 0%
| Agent Tracing Integration | Tên người | Integrate Langfuse/Phoenix into the routing backend to monitor and log agent reasoning steps. |  |  | 0 | 0%
6 | Generation and Verification Module
| Context Assembly & Prompt Specs | Tên người | Standardized Prompt Template documentation managing structural constraints for the generator LLM. |  |  | 0 | 0%
| Citation-Enforced Prompting | Tên người | Advanced instruction system forcing the LLM to append verifiable citation tags to every answer. |  |  | 0 | 0%
| Ragas Evaluation Setup | Tên người | Benchmark pipeline computing 3 core metrics: Faithfulness, Context Precision, and Answer Relevance. |  |  | 0 | 0%
|  | Tên người |  |  |  | 0 | 0%
6 | Citation-Enforced Prompting
|  | Tên người |  |  |  | 0 | 0%
|  | Tên người |  |  |  | 0 | 0%
|  | Tên người |  |  |  | 0 | 0%
|  | Tên người |  |  |  | 0 | 0%
7 | Cross-check Output
| Post-Gen Citation Parser | Tên người | String extraction layer (Regex Parser) tracking out citation mentions from raw LLM output blocks. |  |  | 0 | 0%
| Algorithmic Verification Engine | Tên người | Automated algorithmic audit cross-checking generated citation IDs against ground truth database payloads. |  |  | 0 | 0%
| Automated Re-generation Trigger | Tên người | Production interceptor logic: Silently halting outputs and firing re-generation loops if hallucinated tags occur. |  |  | 0 | 0%
8 | Human in the Loop
| Expert Evaluation & Blind Review | Tên người | A dedicated Streamlit/NextJS dashboard for legal experts to view Query, Context, LLM Answer, and vote/edit citations. |  |  | 0 | 0%
| Expert Evaluation & Blind Review | Tên người | Execution of human audits on the 100 Gold Standard queries by legal peers/professors. |  |  | 0 | 0%
| Inter-Annotator Agreement (IAA) | Tên người | Mathematical calculation of Cohen’s/Fleiss' Kappa to scientifically prove human evaluation consistency. |  |  | 0 | 0%
| Feedback Loop & Knowledge Patching | Tên người | Automated pipeline script that takes human-corrected citations and overwrites/patches the Graph (Neo4j) or Vector DB (Qdrant). |  |  | 0 | 0%
9 | Others
[6 empty] | 0 | 0%
[6 empty] | 0 | 0%
[6 empty] | 0 | 0%
[6 empty] | 0 | 0%
[6 empty] | 0 | 0%
[6 empty] | 0 | 0%
[6 empty] | 0 | 0%

## Evaluation
| Runner | To do | Dense | Sparse | Graph | RRF Fusion | Global Reranker | Generator | Proposed Metrics | Deadline
Ablation 1: Chunk-only vs Chunk+Meta | Thảo | Chunk-only | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE
| Thảo | Chunk+Metadata | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE
Ablation 2: Dense vs Hybrid Graph vs Hybrid+Graph | Kiệt | Retrieval Dense Only | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE
| Bình | BM25 | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE
| Kiệt | Retrieval Hybrid (Sparse+Dense) | TRUE | TRUE | FALSE | FALSE | FALSE | TRUE
|  | Retrieval Dense + Graph | TRUE | FALSE | TRUE | FALSE | FALSE | TRUE
|  | Retrieval Hybrid (Sparse+Dense) + Graph | TRUE | TRUE | TRUE | FALSE | FALSE | TRUE
Ablation 3: Reranker | Kiệt | Rerank-None-Hybrid | TRUE | TRUE | FALSE | FALSE | FALSE | TRUE
| Kiệt | Rerank-RRF-Hybrid | TRUE | TRUE | FALSE | TRUE | FALSE | TRUE
| Kiệt | Rerank-CrossEncoder-Hybrid | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE
| Kiệt | Rerank-RRF+CrossEncoder-Hybrid | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE
Ablation 4: LLM Reasoning |  | Base Reasoning | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
|  | CoT Reasoning | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
|  | Larger Model with Base Reasoning | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
|  | Larger Model with CoT | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
Ablation 3.1: Reranker Choices (Fix Retrieval) |  | RRF for Fusion | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE
|  | Adjust k for RRF or propose another algorithm | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE
|  | Cross Encoder | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE
|  | Study between different cross Encoder | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE
Ablation 5: AI Agents on top of Graph Hybrid RAG |  | Agent with Plain RAG | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
|  | Agent Simple Planner | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
|  | Agent MultiTool Orchestrated | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
|  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
Ablation 6: Citations |  |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE